## Plan till 170913
CTOD List of Modules Resource Allocation Ver 1.1
Sl.No | Modules | ModuleType | Resource | Planned Start Date | Actual Start Date | Planned End Date | Actual End Date | Committed Status | Status as on 09-Sep-13 | Current Status | Comments | Database dependency | Remarks
1 | UI Design | Generic | Raju | 2013-09-02 |  | 2013-09-03 |  | 100 | 100 | 100 |  | No
2 | CSS | Generic | Raju | 2013-09-04 |  | 2013-09-05 |  | 100 | 100 | 100 |  | No
| Search Page | Application | -NA-
3 | Page layout design | Application | Jayant | 2013-09-02 |  | 2013-09-02 |  |  | 100 | 100 |  | No
4 | Progressive filtering | Application | Jayant | 2013-09-03 |  | 2013-09-03 |  | 50 | 100 | 75 | Required Queries not given yet | Yes | Query required
5 | Progressive filtering - Queries | Application | Jayant | 2013-09-04 |  | 2013-09-04 |  |  | 70% | 90 | Required Queries not given yet | Yes | Query required
6 | Chart display | Application | Jayant | 2013-09-05 |  | 2013-09-05 |  |  |  | 100 |  | No
| Search Summary | Application | -NA-
7 | View summary details | Application | Sandeep | 2013-09-02 |  | 2013-09-02 |  | 95 | 95 | 100 |  | No
8 | Save as Public query | Application | Faiyaj | 2013-09-02 |  | 2013-09-02 |  | 100 | 100 | 100 |  | No
9 | Save as Private query | Application | Faiyaj | 2013-09-02 |  | 2013-09-02 |  | 100 | 100 | 100 |  | No
10 | View Saved Queries Public | Application | Faiyaj | 2013-09-02 |  | 2013-09-02 |  | 100 | 50 | 100 |  | No
11 | View Saved Queries Private | Application | Faiyaj | 2013-09-02 |  | 2013-09-02 |  | 100 | 40 | 100 |  | No
| Download query data - Complete | Application | -NA-
12 | Relational format to excel | Application | Sandeep | 2013-09-02 |  | 2013-09-03 |  | 75 | 50 | 80 |  | No
13 | Relational format to CSV | Application | Sandeep | 2013-09-04 |  | 2013-09-05 | [5 empty] | No
14 | Flat file format to excel | Application | Sandeep | 2013-09-05 |  | 2013-09-06 |  | 50 | 25 |  | Required Queries not given yet | Yes | Query required
15 | Flat file format to CSV | Application | Sandeep | 2013-09-10 |  | 2013-09-11 | [5 empty] | Yes | Need to discuss
| Download query data - Custom | Application | -NA-
16 | Relational format to excel | Application | Faiyaj | 2013-09-11 |  | 2013-09-11 |  |  |  | 40 |  | No
17 | Relational format to CSV | Application | Faiyaj | 2013-09-11 |  | 2013-09-11 |  |  |  | 40 |  | No
18 | Flat file format to excel | Application | Faiyaj | 2013-09-12 |  | 2013-09-12 | [5 empty] | Yes | Need to discuss
19 | Flat file format to CSV | Application | Faiyaj | 2013-09-13 |  | 2013-09-13 | [5 empty] | Yes | Need to discuss
| Archive Search data | Application | -NA-
20 | Save data to excel in application | Application | Ashok | 2013-09-03 |  | 2013-09-03
21 | View Archive data | Application | Ashok | 2013-09-03 |  | 2013-09-04
| Study Details | Application | -NA-
22 | View Study details report | Application | Faiyaj | 2013-09-02 |  | 2013-09-04 |  |  | 100 | 100 |  | No
23 | Secondary filters | Application | Jayant | 2013-09-04 |  | 2013-09-04 | [5 empty] | Yes | Query required
24 | Export data to Excel | Application | Sandeep | 2013-09-11 |  | 2013-09-12 |  |  |  | 50 | Required Queries not given yet | Yes | Query required
25 | Export data to CSV | Application | Sandeep | 2013-09-12 |  | 2013-09-13 | [5 empty] | Yes
| View Results | Application | -NA-
26 | Show selected source ids | Application | Sandeep | 2013-09-04 |  | 2013-09-04 |  |  | 100 | 100 |  | No
27 | Create tabs | Application | Sandeep | 2013-09-04 |  | 2013-09-04 |  |  | 100 | 100 |  | No
28 | Display Publication data | Application | Sandeep | 2013-09-05 |  | 2013-09-05 |  |  | 100 | 100 |  | No
29 | Display Publication Trial design data | Application | Sandeep | 2013-09-06 |  | 2013-09-06 |  |  | 100 | 100 |  | No
30 | Export selected source id - Excel | Application | Ashok | 2013-09-10 |  | 2013-09-10
31 | Export selected source id - CSV | Application | Ashok | 2013-09-10 |  | 2013-09-11
32 | Export all source ids - Excel | Application | Ashok | 2013-09-11 |  | 2013-09-11
33 | Export all source ids - CSV | Application | Ashok | 2013-09-10 |  | 2013-09-10
| Create Template | Application | -NA-
34 | Template page design | Application | Faiyaj | 2013-09-03 |  | 2013-09-04 |  | 95 | 100 | 100 |  | No
35 | Save template as public or private | Application | Faiyaj | 2013-09-05 |  | 2013-09-05 |  | 85 | 100 | 100 |  | No
36 | View saved templates | Application | Faiyaj | 2013-09-06 |  | 2013-09-06 |  | 30 | 100 | 100 |  | No
| View Specification | Application | -NA-
37 | View Specification | Application | Faiyaj | 2013-09-11 |  | 2013-09-11 |  | 100 | 100 | 100 |  | No
38 | View specification details | Application | Faiyaj | 2013-09-12 |  | 2013-09-12 |  |  | 100 | 100 |  | No
| Indication Summary | Application | -NA-
39 | Load indications | Application | Jayant | 2013-09-05 |  | 2013-09-05 |  |  | 100 | 100 |  | No
40 | Load indications group by fields | Application | Jayant | 2013-09-05 |  | 2013-09-05 |  |  | 100 | 40 | Required Queries not given yet | Yes | Query required
41 | Show column chart for no. of articles in indication | Application | Jayant | 2013-09-06 |  | 2013-09-06 |  |  | 100 | 100 |  | No
42 | Show summary details | Application | Jayant | 2013-09-09 |  | 2013-09-09 |  |  |  | 100 |  | No
43 | Show column chart for selcted indication & group by field | Application | Jayant | 2013-09-10 |  | 2013-09-10 |  |  | 100 | 20 | Required Queries not given yet | Yes | Query required
44 | Export to word | Application | Faiyaj | 2013-09-10 |  | 2013-09-10 | [5 empty] | No
45 | Export to excel | Application | Jayant | 2013-09-12 |  | 2013-09-12 | [5 empty] | No
46 | Task on Search criteria (Dao Class) | Application | Ashok | 2013-09-04 |  | 2013-09-05 |  |  | 100 | 95 |  | No
47 | Create Links | Application | Sandeep | 2013-09-05 |  | 2013-09-05 |  |  | 70 | 70 | Kept on hold for now | No
48 | Search criteria (Modal Class) | Application | Ashok | 2013-09-06 |  | 2013-09-06 |  |  | 100 | 100 |  | No
49 | Client Validation on login and Registration | Application | Ashok | 2013-09-07 |  | 2013-09-08 |  |  | 80 | 80 |  | No
50 | Show User Details (User Management) | Application | Satish | 2013-09-07 |  | 2013-09-07 |  |  | 100 | 85 |  | No
51 | Send email on Registration. | Application | Ashok | 2013-09-09 |  | 2013-09-09 |  |  | 100 | 80 |  | No
52 | View Result. | Application | Sandeep | 2013-09-09 |  | 2013-09-10 |  |  | 100 | 100 |  | No
53 | User Authentication | Generic | Ashok | 2013-09-10 |  | 2013-09-10 |  |  | 100 | 75 |  | No

## Plan from 190913
2013-09-19
CTOD List of Modules Resource Allocation Ver 1.2
Sl.No | Main Module | Modules | ModuleType | Resource | Status as on 16-09-13 in (%) | Dev Hrs | Planned Start Date | Actual Start Date | Planned End Date | Actual End Date | Status | Comments | Database dependency
1 | UI | UI Design | Generic | Raju | 90 | 8 | 2013-09-19 |  | 2013-09-19 |  |  |  | No
2 | UI | CSS | Generic | Raju | 100 | [7 empty] | No
3 | UI | Create Navigation | Application | Faiyaj | 0 | 18 | 2013-09-25 |  | 2013-09-26
4 | Search Page | Page layout design | Application | Jayant | 100 | [7 empty] | No
5 | Search Page | Progressive filtering | Application | Jayant | 75 | 32 | 2013-09-24 |  | 2013-09-27 |  |  | Required Queries from DB | Yes
6 | Search Page | Progressive filtering - Queries | Application | Jayant | 90 | 32 | 2013-09-30 |  | 2013-10-03 |  |  | Required Queries from DB | Yes
7 | Search Page | Chart display | Application | Jayant | 100 | [7 empty] | No
8 | Search Summary | View summary details | Application | Sandeep | 100 | [7 empty] | No
9 | Search Summary | Save as Public query | Application | Faiyaj | 100 | [7 empty] | No
10 | Search Summary | Save as Private query | Application | Faiyaj | 100 | [7 empty] | No
11 | Search Summary | View Saved Queries Public | Application | Faiyaj | 100 | [7 empty] | No
12 | Search Summary | View Saved Queries Private | Application | Faiyaj | 100 | [7 empty] | No
13 | Search Summary | Download query data - Complete -Relational format to excel | Application | Sandeep | 80 | 32 | 2013-09-19 |  | 2013-09-24 |  | In Progress |  | No
14 | Search Summary | Download query data - Complete- Relational format to CSV | Application | Sandeep | 0 | 32 | 2013-09-25 |  | 2013-09-30 |  |  |  | No
15 | Search Summary | Download query data - Complete - Flat file format to excel | Application | Sandeep | 0 | 24 | 2013-10-01 |  | 2013-10-03 |  |  | Required Queries from DB | Yes
16 | Search Summary | Download query data - Complete - Flat file format to CSV | Application | Sandeep | 0 | 24 | 2013-10-04 |  | 2013-10-08 |  |  |  | Yes
17 | Search Summary | Download query data - Custom - Relational format to excel | Application | Sandeep | 40 | 32 | 2013-10-09 |  | 2013-10-14 |  |  |  | No
18 | Search Summary | Download query data - Custom - Relational format to CSV | Application | Sandeep | 40 | 32 | 2013-10-15 |  | 2013-10-18 |  |  |  | No
19 | Search Summary | Download query data - Custom - Flat file format to excel | Application | Sandeep | 0 | 24 | 2013-10-21 |  | 2013-10-23 |  |  |  | Yes
20 | Search Summary | Download query data - Custom - Flat file format to CSV | Application | Sandeep | 0 | 24 | 2013-10-24 |  | 2013-10-28 |  |  |  | Yes
21 | Search Summary | Archive Search data - Save data to excel in application | Application | Faiyaj | 0 | 40 | 2013-09-27 |  | 2013-10-03
22 | Search Summary | Archive Search data - View Archive data | Application | Faiyaj | 0 | 32 | 2013-10-04 |  | 2013-10-09
23 | Study Details | View Study details report | Application | Faiyaj | 100 | [7 empty] | No
24 | Study Details | Secondary filters | Application | Jayant | 0 | 32 | 2013-10-04 |  | 2013-10-09 |  |  |  | Yes
25 | Study Details | Export data to Excel | Application | Sandeep | 50 | 24 | 2013-10-29 |  | 2013-10-31 |  |  | Required Queries from DB | Yes
26 | Study Details | Export data to CSV | Application | Sandeep | 0 | 24 | 2013-11-01 |  | 2013-11-05 |  |  |  | Yes
27 | View Results | Show selected source ids | Application | Sandeep | 100 | [7 empty] | No
28 | View Results | Create tabs | Application | Sandeep | 100 | [7 empty] | No
29 | View Results | Display Publication data | Application | Sandeep | 100 | [7 empty] | No
30 | View Results | Display Publication Trial design data | Application | Sandeep | 100 | [7 empty] | No
31 | View Results | Export selected source id - Excel | Application | Faiyaj | 0 | 24 | 2013-10-10 |  | 2013-10-14
32 | View Results | Export selected source id - CSV | Application | Faiyaj | 0 | 24 | 2013-10-15 |  | 2013-10-17
33 | View Results | Export all source ids - Excel | Application | Faiyaj | 0 | 24 | 2013-10-18 |  | 2013-10-22
34 | View Results | Export all source ids - CSV | Application | Faiyaj | 0 | 24 | 2013-10-23 |  | 2013-10-25
35 | Create Template | Template page design | Application | Faiyaj | 100 | [7 empty] | No
36 | Create Template | Save template as public or private | Application | Faiyaj | 100 | [7 empty] | No
37 | Create Template | View saved templates | Application | Faiyaj | 100 | [7 empty] | No
38 | View Specification | View Specification | Application | Faiyaj | 100 | [7 empty] | No
39 | View Specification | View specification details | Application | Faiyaj | 100 | [7 empty] | No
40 | Indication Summary | Load indications | Application | Jayant | 100 | [7 empty] | No
41 | Indication Summary | Load indications group by fields | Application | Jayant | 40 | 10 | 2013-10-10 |  | 2013-10-10 |  |  | Required Queries from DB | Yes
42 | Indication Summary | Show column chart for no. of articles in indication | Application | Jayant | 100 | [7 empty] | No
43 | Indication Summary | Show summary details | Application | Jayant | 100 | [7 empty] | No
44 | Indication Summary | Show column chart for selcted indication & group by field | Application | Jayant | 20 | 30 | 2013-10-11 |  | 2013-10-15 |  |  | Required Queries from DB | Yes
45 | Indication Summary | Export to word | Application | Faiyaj | 0 | 24 | 2013-10-28 |  | 2013-10-30 |  |  |  | No
46 | Indication Summary | Export to excel | Application | Jayant | 0 | 24 | 2013-10-16 |  | 2013-10-18 |  |  |  | No
47 | User Management | Create User | Application | Lokesh | 70 | 40 | 2013-09-19 |  | 2013-09-25 |  | In Progress | Kept on hold for now | No
48 | User Management | Send email on Registration. |  | Lokesh | 0 | 16 | 2013-09-26 |  | 2013-09-27
49 | User Management | Show User Details | Application | Ashok | 0 | 12 | 2013-09-19 |  | 2013-09-20 |  | Completed |  | No
50 | User Management | Edit/Delete User | Application | Ashok | 0 | 12 | 2013-09-23 |  | 2013-09-23 |  | In Progress |  | No
51 | User Management | Create Roles | Application | Ashok | 0 | 16 | 2013-09-24 |  | 2013-09-25 |  |  |  | No
52 | User Management | View Roles | Application | Ashok | 0 | 16 | 2013-09-26 |  | 2013-09-30
53 | User Management | Assign User Roles | Application | Ashok | 0 | 16 | 2013-10-01 |  | 2013-10-02
54 | User Management | Role based application access | Application | Lokesh | 0 | 16 | 2013-09-30 |  | 2013-10-01
55 | User Management | Problem in sign in | Application | Ashok | 0 | 40 | 2013-10-03 |  | 2013-10-09
56 | User Management | Change password | Application | Ashok | 0 | 20 | 2013-10-10 |  | 2013-10-14
57 | User Management | User Authentication | Application | Lokesh | 75 | 16 | 2013-10-02 |  | 2013-10-03 |  |  |  | No
[8 empty] | Target Completion Date | 2013-11-05
[8 empty] | Leaves | 10
[8 empty] | Holidays | 3
[8 empty] | Actual Completion Date | 2013-11-22
Formulas:
Planned Start Date = WORKDAY([Planned End Date, row above],1)
Planned End Date = WORKDAY([Planned Start Date]-1,[Dev Hrs]/8)
Planned End Date = WORKDAY([Planned Start Date],[Dev Hrs]/8)
Note on H4: satish.palli: Lokesh Effort User mgmt - as per my est