## Sheet1
|  | Start Date | 2013-09-20 | 8.5
Module Name | Method/Screen name | Screen | Business Methods | Total | Resource | Planned Start Date | Actual Start Date | Planned End Date | Actual End Date
Login Authentication-Application | UserAuthentication | 4 | 6 | 10 | 1 | 2013-09-20 |  | 2013-09-20
UserManagement | CreateUser | 32 | 16 | 48 | 1 | 2013-09-23 |  | 2013-09-30
UserManagement | ViewUser | 16 | 32 | 48 | 1 | 2013-10-01 |  | 2013-10-08
UserManagement | EditUser | 16 | 16 | 32 | 1 | 2013-10-09 |  | 2013-10-14
Search Primary | Search Progressive Filtering - Indication | 32 | 32 | 64 | 2 | 2013-09-20 |  | 2013-10-01
Search Primary | Search Progressive Filtering - Trial Filters | 16 | 32 | 48 | 2 | 2013-10-02 |  | 2013-10-09
Search Primary | Search Progressive Filtering - Treatment Class | 8 | 16 | 24 | 2 | 2013-10-10 |  | 2013-10-14
Search Primary | Search Progressive Filtering - Treatment Name |  | 16 | 16 | 2 | 2013-10-15 |  | 2013-10-16
Search Primary | Search Progressive Filtering - Inclusion Criteria |  | 16 | 16 | 2 | 2013-10-17 |  | 2013-10-18
Search Primary | GetInclusionCriteriaValues |  | 10 | 10 | 2 | 2013-10-21 |  | 2013-10-22
Search Primary | Search Progressive Filtering - Assessment values |  | 16 | 16 | 2 | 2013-10-23 |  | 2013-10-24
Search Primary | BindChartData |  | 10 | 10 | 2 | 2013-10-25 |  | 2013-10-28
SearchSummary | GetSummaryDetails | 32 | 16 | 48 | 3 | 2013-09-26 |  | 2013-10-03
SearchSummary | BindSummaryDetails | 16 | 3 | 19 | 3 | 2013-10-04 |  | 2013-10-08
SearchSummary | SaveAsPrivateQuery | 11.2 | 10 | 21.2 | 3 | 2013-10-09 |  | 2013-10-11
SearchSummary | SaveAsPrivateQuery | 5.6 | 5 | 10.6 | 3 | 2013-10-14 |  | 2013-10-15
SearchSummary | Complete Relational Format export - Excel - Get Data |  | 32 | 32 | 3 | 2013-10-16 |  | 2013-10-21
SearchSummary | Complete Relational Format export - Excel - WriteDataToExcel |  | 32 | 32 | 3 | 2013-10-22 |  | 2013-10-25
SearchSummary | Complete Flat File Format export - Excel - Get Data |  | 32 | 32 | 3 | 2013-10-28 |  | 2013-10-31
SearchSummary | Complete Flat File Format export - Excel - WriteDataToExcel |  | 32 | 32 | 3 | 2013-11-01 |  | 2013-11-06
SearchSummary | Custom Relational Format export - Excel - Get Data |  | 32 | 32 | 3 | 2013-11-07 |  | 2013-11-12
SearchSummary | Custom Relational Format export - Excel - WriteDataToExcel |  | 32 | 32 | 3 | 2013-11-13 |  | 2013-11-18
SearchSummary | Custom Flat File Format export - Excel - Get Data |  | 22.4 | 22.4 | 3 | 2013-11-19 |  | 2013-11-21
SearchSummary | Custom Flat File Format export - Excel - WriteDataToExcel |  | 32 | 32 | 3 | 2013-11-22 |  | 2013-11-27
SearchSummary | Archive Data: GetArchiveData |  | 32 | 32 | 1 | 2013-10-15 |  | 2013-10-18
SearchSummary | Archive Data: CreateArchiveData to Excel |  | 32 | 32 | 1 | 2013-10-21 |  | 2013-10-24
SearchSummary | Archive Data: Save ArchiveExcel data to user account |  | 10 | 10 | 1 | 2013-10-25 |  | 2013-10-28
Search:View Study Details | GetStudyDetails | 32 | 16 | 48 | 2 | 2013-10-29 |  | 2013-11-05
Search:View Study Details | BindStudyDetails |  | 6 | 6 | 2 | 2013-11-06 |  | 2013-11-06
Search:View Study Details | ExcelExport: GetSelectedData |  | 10 | 10 | 2 | 2013-11-07 |  | 2013-11-08
Search:View Study Details | WriteData to Excel |  | 32 | 32 | 2 | 2013-11-11 |  | 2013-11-14
Search:View Study Details | GetSecondaryFiltersData |  | 16 | 16 | 2 | 2013-11-15 |  | 2013-11-18
Search:ViewResults | GetSourceIds | 32 | 10 | 42 | 4 | 2013-10-21 |  | 2013-10-25
Search:ViewResults | GetPublicationData | 24 | 10 | 34 | 4 | 2013-10-28 |  | 2013-11-01
Search:ViewResults | GetTrialDesign_TrialLevelInformation | 16 | 16 | 32 | 4 | 2013-11-04 |  | 2013-11-07
Search:ViewResults | GetTrialDesign_Inclusion | 11.2 | 6 | 17.2 | 4 | 2013-11-08 |  | 2013-11-12
Search:ViewResults | ViewResults:GetArmData | 16.8 | 3 | 19.8 | 4 | 2013-11-13 |  | 2013-11-15
Search:ViewResults | ViewResults:BindTreatmentArms_Interventions_GetTreatment | 16 | 3 | 19 | 4 | 2013-11-18 |  | 2013-11-20
Search:ViewResults | ViewResults:BindTreatmentArms_Interventions_Planned | 11.2 | 3 | 14.2 | 4 | 2013-11-21 |  | 2013-11-22
Search:ViewResults | ViewResults:BindTreatmentArms_Interventions_Actual | 5.6 | 3 | 8.6 | 4 | 2013-11-25 |  | 2013-11-26
Search:ViewResults | ViewResults:BindTreatmentArms_OtherInterventions_InterventionType | 16 | 3 | 19 | 4 | 2013-11-27 |  | 2013-11-29
Search:ViewResults | ViewResults:BindTreatmentArms_OtherInterventions_InterventionTypeFactor | 32 | 3 | 35 | 4 | 2013-12-02 |  | 2013-12-06
Search:ViewResults | ViewResults:BindTreatmentArms_PatientCharacteristics |  | 3 | 3 | 4 | 2013-12-09 |  | 2013-12-09
Search:ViewResults | ViewResults:BindTreatmentArms_Outcomes |  | 3 | 3 | 4 | 2013-12-10 |  | 2013-12-10
ViewArchiveData | GetArchiveData | 24 | 10 | 34 | 1 | 2013-10-29 |  | 2013-11-04
ViewArchiveData | DownloadArchiveDataToExcel |  | 10 | 10 | 1 | 2013-11-05 |  | 2013-11-06
ViewSavedQueries | ViewSavedQueries-GetPublicQueries | 16 | 3 | 19 | 1 | 2013-11-07 |  | 2013-11-11
ViewSavedQueries | ViewSavedQueries-GetPrivateQueries | 8 | 3 | 11 | 1 | 2013-11-12 |  | 2013-11-13
CreateTemplate | CreateTemplate-GetTemplateData_Public | 32 | 16 | 48 | 1 | 2013-11-14 |  | 2013-11-21
CreateTemplate | CreateTemplate-GetTemplateData_Public | 16 | 4.8 | 20.8 | 1 | 2013-11-22 |  | 2013-11-26
CreateTemplate | SaveTemplate-Public | 16 | 6 | 22 | 1 | 2013-11-27 |  | 2013-11-29
CreateTemplate | SaveTemplate-Private |  | 3 | 3 | 1 | 2013-12-02 |  | 2013-12-02
ViewTemplate | ViewTemplate-GetPublicData | 16 | 6 | 22 | 1 | 2013-12-03 |  | 2013-12-05
ViewTemplate | ViewTemplate-GetPrivateData | 6.4 | 6 | 12.4 | 1 | 2013-12-06 |  | 2013-12-09
ViewSpecification | GetExportSpecificationData-Word | 16 | 16 | 32 | 2 | 2013-11-19 |  | 2013-11-22
ViewSpecification | GetExportSpecificationData-Excel | 32 | 8 | 40 | 2 | 2013-10-28 |  | 2013-11-01
ViewSpecificationDetails | ViewSpecificationDetails-GetSpecificationData | 32 | 6 | 38 | 2 | 2013-11-04 |  | 2013-11-08
ViewSpecificationDetails | ViewSpecificationDetails-AddSpecificationData | 32 | 10 | 42 | 2 | 2013-11-08 |  | 2013-11-14
ViewSpecificationDetails | ViewSpecificationDetails-GetInclusionData |  | 10 | 10 | 2 | 2013-11-13 |  | 2013-11-14
ViewSpecificationDetails | ViewSpecificationDetails-AddInclusionData |  | 6 | 6 | 2 | 2013-11-18 |  | 2013-11-18
ViewSpecificationDetails | ViewSpecificationDetails-GetPatientCharacteristics |  | 10 | 10 | 2 | 2013-11-21 |  | 2013-11-22
ViewSpecificationDetails | ViewSpecificationDetails-AddPatientCharacteristics |  | 10 | 10 | 2 | 2013-11-25 |  | 2013-11-26
ViewSpecificationDetails | ViewSpecificationDetails-GetOutcomeData |  | 6 | 6 | 2 | 2013-11-27 |  | 2013-11-27
ViewSpecificationDetails | ViewSpecificationDetails-AddOutcomeData |  | 6 | 6 | 2 | 2013-12-02 |  | 2013-12-02
IndicationSummary | ViewIndicationSummary-GetOverviewData | 8 | 3 | 11 | 2 | 2013-12-09 |  | 2013-12-10
IndicationSummary | ViewIndicationSummary-ByIndication | 16 | 10 | 26 | 3 | 2013-11-28 |  | 2013-12-03
IndicationSummary | ViewIndicationSummary-ByTreatment | 12.8 | 7 | 19.8 | 3 | 2013-12-04 |  | 2013-12-06
IndicationSummary | ViewIndicationSummary-ByDrugclass | 12.8 | 7 | 19.8 | 3 | 2013-12-09 |  | 2013-12-11
IndicationSummary | ViewIndicationSummary-ByEndpoint | 12.8 | 7 | 19.8 | 3 | 2013-12-12 |  | 2013-12-16
IndicationSummary | ViewIndicationSummary-BySamplesize | 12.8 | 7 | 19.8 | 3 | 2013-12-17 |  | 2013-12-19
|  | 723.2 | 915.2 | 1638.4
Formulas:
Planned Start Date = WORKDAY([Planned End Date, row above],1)
Planned End Date = WORKDAY([Planned Start Date],([Total]/8.5)-1)
Planned End Date = WORKDAY([Planned Start Date],([Total]/F1))

## Sheet2
Resource
Sl.No | Candidate | Emp. Type | Status | On Project
1 | Lokesh | Contract | Joined on 10-Sep-2013 | 2013-09-20 | 1
2 | Sandeep |  |  | 2013-09-20 | 2
3 | Khader Phasha | Contract | Joined 19-Sep-2013
4 | Nagaraju | Contract | Joined 25-Sep-2013
5 | Praveen | FTE | Joined on 10-Oct-2013 | 2013-10-21 | 5
6 | Manoj | FTE | will join on 21-Oct-13
7 | S Manisri | Not Joined
8 | Ramu voora | Not yet finalized
9 | Ashok | FTE | Joined, but not reporting since 07-Oct-13 | 2013-09-26 | 3
| Jayant |  |  | 2013-10-07 | 3A | ashok task assigned
| Sandeep |  |  | 2013-10-07 | 4

## Sheet3
| PlannedStartDate | Actual Start Date | Planned End Date | Actual End Date | Status | weeks
Requirements |  |  |  | 2013-09-19
Build | 2013-09-20 | 2013-10-01 | 2013-12-16 |  |  | 8 | 14
IT | 2013-12-17 |  | 2014-01-07 |  |  | 3
ST | 2014-01-08 |  | 2014-01-29 |  |  | 3
UAT | 2014-01-30 |  | 2014-02-20 |  |  | 3
Formulas:
Planned End Date = WORKDAY([Actual Start Date],(8*5)+14)
Planned End Date = WORKDAY([PlannedStartDate],(3*5))
PlannedStartDate = WORKDAY([Planned End Date, row above],1)
Note on J5: satish.palli: 4 holidays, 10 leaves